## Sheet1
| Start date | 2024-04-18 | This is only a suggested timeline to be used in combination with the call specific EC application template. This draft timeline is based on previous application experience and commonly missed sections. Following this draft structure of the time distribution until submission, minimize the risk of failure in key section.
| Application Deadline | 2025-12-20 | [11 empty] | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Timeline
TO-DO |  | Progress | Start of proposal writing | [8 empty] | Submission deadline
Identify Core researchers involved | - |  | x
Download application specific template for part B
Contact RSO and discuss the level of support needed | - |  |  | y | [8 empty] | OPTIONAL: annotated template meeting with RSO + alignment meeting
Register on EC portal | -
Contact school financial department | -
Table: Key Elements of the impact section | 2.3 |  |  | y | [8 empty] | OPTIONAL: RSO impact review and feedback
Consortium composition incl value chain and complementary | 3.2 |  |  | x | x
Partner table | Part A |  |  |  | x
Accesess to infrastructure | 3.2 |  |  |  | x
List of Objectives | 1.1 |  |  |  | x
Project’s contribution to the expected outcomes and impacts, should the project be successful | 2.1 |  |  |  | x | x
Draft tasks inkl efort and costs (remember management and CDE tasks) |  |  |  |  | x | x | x
Measures to maximise the impact | 2.1 + 2.2 |  |  |  |  | x | x | y |  |  |  |  | OPTIONAL: RSO impact review and feedback
Industrial/commercial involvement in the project to ensure exploitation of the results | 2.2 |  |  |  |  | x | x
IPR strategy | 2.2 | [5 empty] | x
Beyond the state-of-the-art | 1.1 | [5 empty] | x | x
Budget KTH & Consortium | Part A | [5 empty] | x | x | y |  |  |  | OPTIONAL: RSO budget and consortium light review
National or international research and innovation activities whose results will feed into the project | 1.2 | [6 empty] | x
Ethics desciption | [7 empty] | x | y |  |  |  | OPTIONAL: RSO ethics review
Interdisiplinarity | 1.2 | [6 empty] | x
Open science (FAIR) max 1 page | Part B | [6 empty] | x | x
Work package descriptions | 3.1b | [6 empty] | x | x
List of deliverables | 3.1c | [7 empty] | x
List of Milestones | 3.1d | [7 empty] | x
List of Risks | 3.1e | [7 empty] | x
Timing of the different work packages and their components (Gantt chart or similar); | 3.1 | [7 empty] | x |  |  |  |  | 611
R&I maturity / TRL | 1.1 | [7 empty] | x | x
Graphical presentation of the components showing how they inter-relate (Pert chart or similar). | 3.1 | [7 empty] | x | x | y |  | OPTIONAL: RSO application review and feedback
WP connection and project structure chart | 3.1 | [7 empty] | x | x | x
Methodology | 1.2 | [8 empty] | x | x | y | OPTIONAL: RSO final application review and feedback focus on WP descriptions
Ethics and Security | Part A | [9 empty] | x
Declarations | Part A | [9 empty] | x
Abstract & keywords | Part A | [9 empty] | x | x
Presubmission Review | Part A & B | [10 empty] | x
| 2024-09-09 | 2024-04-18 | 2024-06-18 02:24 | 2024-08-18 04:48 | 2024-10-18 07:12 | 2024-12-18 09:36 | 2025-02-17 12:00 | 2025-04-19 14:24 | 2025-06-19 16:48 | 2025-08-19 19:12 | 2025-10-19 21:36 | 2025-12-20